## Worklogs
Issue Key | Issue summary | Hours | Work date | Username | Full name | Period | Account Key | Account Name | Account Lead | Account Category | Account Customer | Activity Name | Component | All Components | Version Name | Issue Type | Issue Status | Project Key | Project Name | Epic | Epic Link | Work Description | Parent Key | Reporter | External Hours | Billed Hours | Issue Original Estimate | Issue Remaining Estimate | Location Name | Type of Work
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 6.5 | 2026-05-04 | Viera.Mrazova | Viera Mrazova | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP AUTH HBA & IT Audit |  | Zuzana.Benedikova |  | 6.5 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1 | 2026-05-04 09:08 | Gabriela.Princova | Gabriela Princova | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO - INC01482978: Monitoring FI-AA - RE-FX LM: Fehler bei Umbuchung |  | Zuzana.Benedikova |  | 1 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 0.5 | 2026-05-04 09:08 | Gabriela.Princova | Gabriela Princova | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO Rx4 - Status AA Alignment Call |  | Zuzana.Benedikova |  | 0.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-29 | SK - RWE Corporate Solutions 2026 - Roman | 0.5 | 2026-05-04 09:19 | Roman.Kroupa | Roman Kroupa | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | IN PROGRESS | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SM131759 |  | Zuzana.Benedikova |  | 0.5 | 1600 | 1452.5 | Default Location | Create
FHSTRWEPOWK-29 | SK - RWE Corporate Solutions 2026 - Roman | 0.5 | 2026-05-04 09:19 | Roman.Kroupa | Roman Kroupa | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | IN PROGRESS | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SM131738 |  | Zuzana.Benedikova |  | 0.5 | 1600 | 1452.5 | Default Location | Create
FHSTRWEPOWK-29 | SK - RWE Corporate Solutions 2026 - Roman | 1 | 2026-05-04 09:19 | Roman.Kroupa | Roman Kroupa | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | IN PROGRESS | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SM131705 |  | Zuzana.Benedikova |  | 1 | 1600 | 1452.5 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 0.75 | 2026-05-04 09:22 | Gabriela.Princova | Gabriela Princova | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SP6-ID 128162 - Alignment FB/IT |  | Zuzana.Benedikova |  | 0.75 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-28 | SK - RWE Corporate Solutions 2026 - Alzbetka | 0.5 | 2026-05-04 09:46 | KollarcikovaA | Kollarcikova Alzbeta | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | RWE ASC II - Operation Meeting (Managed Services) |  | Zuzana.Benedikova |  | 0.5 | 1600 | 1386 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 1 | 2026-05-04 11:02 | Viera.Mrazova | Viera Mrazova | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP SF Foundation |  | Zuzana.Benedikova |  | 1 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-23 | SK - RWE Corporate Solutions 2026 - Veronika M. | 1 | 2026-05-04 13:24 | Veronika.Mikulakova | Veronika Mikulakova | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | AA Alignment meeting - 1 hod |  | Zuzana.Benedikova |  | 1 | 1600 | 1489 | Default Location | Create
FHSTRWEPOWK-27 | SK - RWE Corporate Solutions 2026 - Dasa | 2 | 2026-05-04 13:48 | Dasa.Krompaska | Dasa Krompaska | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | CITS AddServ RES- SM0000131876 - 2 |  | Zuzana.Benedikova |  | 2 | 1600 | 1329 | Default Location | Create
FHSTRWEPOWK-22 | SK - RWE Corporate Solutions 2026 - Lien | 3 | 2026-05-04 16:03 | lien.nguyenthi | Thi Lien Nguyen | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | INC01490238/Chang: 131783, CC ID not displayed - SNOTE3491207 |  | Zuzana.Benedikova |  | 3 | 1600 | 1560 | Default Location | Create
FHSTRWEPOWK-30 | SK - RWE Corporate Solutions 2026 - Silvia | 6.5 | 2026-05-04 18:53 | Silvia.Horvatova | Silvia Horvatova | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | tax, race |  | Zuzana.Benedikova |  | 6.5 | 1600 | 996.75 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 6.5 | 2026-05-05 | Viera.Mrazova | Viera Mrazova | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP AUTH HBA & IT Audit |  | Zuzana.Benedikova |  | 6.5 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1 | 2026-05-05 09:07 | Gabriela.Princova | Gabriela Princova | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO - Infosession Solution Manager (Agile Delivery Teams) |  | Zuzana.Benedikova |  | 1 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1.5 | 2026-05-05 09:36 | Gabriela.Princova | Gabriela Princova | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO Rx4 - Analyse INC01480850 - Dumps Fiori |  | Zuzana.Benedikova |  | 1.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-28 | SK - RWE Corporate Solutions 2026 - Alzbetka | 1.5 | 2026-05-05 09:51 | KollarcikovaA | Kollarcikova Alzbeta | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | Chapter Controlling / interne Abstimmung, Infosession Solution Manager (Agile Delivery Teams) - Option 1 - DE |  | Zuzana.Benedikova |  | 1.5 | 1600 | 1386 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 1 | 2026-05-05 11:02 | Viera.Mrazova | Viera Mrazova | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP SF Foundation |  | Zuzana.Benedikova |  | 1 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-27 | SK - RWE Corporate Solutions 2026 - Dasa | 2 | 2026-05-05 13:48 | Dasa.Krompaska | Dasa Krompaska | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | CITS/SAP Core Rx4 add.Serv.- Meetings - 2 |  | Zuzana.Benedikova |  | 2 | 1600 | 1329 | Default Location | Create
FHSTRWEPOWK-22 | SK - RWE Corporate Solutions 2026 - Lien | 1 | 2026-05-05 16:05 | lien.nguyenthi | Thi Lien Nguyen | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | 131705, Cytric Reisekosten-Report UK |  | Zuzana.Benedikova |  | 1 | 1600 | 1560 | Default Location | Create
FHSTRWEPOWK-30 | SK - RWE Corporate Solutions 2026 - Silvia | 8 | 2026-05-05 18:53 | Silvia.Horvatova | Silvia Horvatova | 0426 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | tax, race |  | Zuzana.Benedikova |  | 8 | 1600 | 996.75 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 6.5 | 2026-05-06 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP AUTH HBA & IT Audit |  | Zuzana.Benedikova |  | 6.5 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1 | 2026-05-06 09:16 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO Rx1 - Object Analyses - JIVs for RWE Intern |  | Zuzana.Benedikova |  | 1 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 0.5 | 2026-05-06 09:18 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | Rx4 Analyse Neue BWA Z17 – Abgang mit Erlös §6b Rücklage Grundstücke |  | Zuzana.Benedikova |  | 0.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1 | 2026-05-06 09:20 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO Rx4 - INC01482978: Monitoring FI-AA - RE-FX LM: Fehler bei Umbuchung -> Re-Test |  | Zuzana.Benedikova |  | 1 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 1 | 2026-05-06 11:02 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP SF Foundation |  | Zuzana.Benedikova |  | 1 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-27 | SK - RWE Corporate Solutions 2026 - Dasa | 2 | 2026-05-06 13:48 | Dasa.Krompaska | Dasa Krompaska | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | CITS AddServ RWE AG- SM0000131876 |  | Zuzana.Benedikova |  | 2 | 1600 | 1329 | Default Location | Create
FHSTRWEPOWK-30 | SK - RWE Corporate Solutions 2026 - Silvia | 7 | 2026-05-06 18:53 | Silvia.Horvatova | Silvia Horvatova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | tax, race |  | Zuzana.Benedikova |  | 7 | 1600 | 996.75 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 6.5 | 2026-05-07 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP AUTH HBA & IT Audit |  | Zuzana.Benedikova |  | 6.5 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 0.75 | 2026-05-07 09:13 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | GLOBAL SP6-ID 131824 FI-AA: New KeyFigure Group Z001 |  | Zuzana.Benedikova |  | 0.75 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1.25 | 2026-05-07 09:14 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO INC01493961 RP4_100 RE-FX/AA: Datum ÜWE auslösen (Liegenschaftsmanagement) - Fehler Mengenermittlung |  | Zuzana.Benedikova |  | 1.25 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 1 | 2026-05-07 11:02 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP SF Foundation |  | Zuzana.Benedikova |  | 1 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-31 | SK - RWE Corporate Solutions 2026 - Kubo | 2 | 2026-05-07 12:23 | Jakub.Martinek | Jakub Martinek | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | INC01482978 |  | Zuzana.Benedikova |  | 2 | 1600 | 1542 | Default Location | Create
FHSTRWEPOWK-27 | SK - RWE Corporate Solutions 2026 - Dasa | 4 | 2026-05-07 13:48 | Dasa.Krompaska | Dasa Krompaska | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | CITS AddServ RES- SM0000131876- 2 CITS AddServ Power- SM0000126399- 2 |  | Zuzana.Benedikova |  | 4 | 1600 | 1329 | Default Location | Create
FHSTRWEPOWK-30 | SK - RWE Corporate Solutions 2026 - Silvia | 3 | 2026-05-07 18:52 | Silvia.Horvatova | Silvia Horvatova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | tax, race |  | Zuzana.Benedikova |  | 3 | 1600 | 996.75 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 0.5 | 2026-05-08 09:09 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO Rx4 INC01480850: FIORI RWE Asset History Sheet Extension |  | Zuzana.Benedikova |  | 0.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 2 | 2026-05-08 09:12 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | GLOBAL SP6-ID 131824 FI-AA: New KeyFigure Group Z001 |  | Zuzana.Benedikova |  | 2 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-28 | SK - RWE Corporate Solutions 2026 - Alzbetka | 3 | 2026-05-08 10:07 | KollarcikovaA | Kollarcikova Alzbeta | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | INC01458819 |  | Zuzana.Benedikova |  | 3 | 1600 | 1386 | Default Location | Create
FHSTRWEPOWK-27 | SK - RWE Corporate Solutions 2026 - Dasa | 4 | 2026-05-08 14:04 | Dasa.Krompaska | Dasa Krompaska | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | GSTPOPS-42420 - 2 GSTPOPS-45454 - 2 |  | Zuzana.Benedikova |  | 4 | 1600 | 1329 | Default Location | Create
FHSTRWEPOWK-30 | SK - RWE Corporate Solutions 2026 - Silvia | 8 | 2026-05-08 18:52 | Silvia.Horvatova | Silvia Horvatova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | tax, race |  | Zuzana.Benedikova |  | 8 | 1600 | 996.75 | Default Location | Create
FHSTRWEPOWK-29 | SK - RWE Corporate Solutions 2026 - Roman | 1 | 2026-05-11 09:19 | Roman.Kroupa | Roman Kroupa | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | IN PROGRESS | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SM130853 |  | Zuzana.Benedikova |  | 1 | 1600 | 1452.5 | Default Location | Create
FHSTRWEPOWK-23 | SK - RWE Corporate Solutions 2026 - Veronika M. | 1 | 2026-05-11 10:00 | Veronika.Mikulakova | Veronika Mikulakova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | Alignment meeting regarding 131824 - 1 hod |  | Zuzana.Benedikova |  | 1 | 1600 | 1489 | Default Location | Create
FHSTRWEPOWK-30 | SK - RWE Corporate Solutions 2026 - Silvia | 8 | 2026-05-11 10:29 | Silvia.Horvatova | Silvia Horvatova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | race, tax |  | Zuzana.Benedikova |  | 8 | 1600 | 996.75 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 1 | 2026-05-11 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP SF |  | Zuzana.Benedikova |  | 1 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 6.5 | 2026-05-11 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP AUTH HBA & IT Audit |  | Zuzana.Benedikova |  | 6.5 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1.5 | 2026-05-11 13:34 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | GLOBAL SP6-ID 131824 FI-AA: New KeyFigure Group Z001 |  | Zuzana.Benedikova |  | 1.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-27 | SK - RWE Corporate Solutions 2026 - Dasa | 2 | 2026-05-11 13:49 | Dasa.Krompaska | Dasa Krompaska | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | CITS AddServ RES- SM0000131876 - 2 |  | Zuzana.Benedikova |  | 2 | 1600 | 1329 | Default Location | Create
FHSTRWEPOWK-28 | SK - RWE Corporate Solutions 2026 - Alzbetka | 0.5 | 2026-05-11 15:08 | KollarcikovaA | Kollarcikova Alzbeta | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | RWE ASC II - Operation Meeting (Managed Services) |  | Zuzana.Benedikova |  | 0.5 | 1600 | 1386 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 0.5 | 2026-05-11 15:18 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | Global SP6-ID 131985 FI-AA: Erweiterung RWE FIORI Asset Histo - Extention; Asset-History-Sheet - Analyse / PS-Fields |  | Zuzana.Benedikova |  | 0.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1.5 | 2026-05-11 15:20 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO Rx4 - INC01480850 - Dumps Analyse RS4_100 |  | Zuzana.Benedikova |  | 1.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-29 | SK - RWE Corporate Solutions 2026 - Roman | 1 | 2026-05-12 09:19 | Roman.Kroupa | Roman Kroupa | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | IN PROGRESS | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SM130853 |  | Zuzana.Benedikova |  | 1 | 1600 | 1452.5 | Default Location | Create
FHSTRWEPOWK-30 | SK - RWE Corporate Solutions 2026 - Silvia | 8 | 2026-05-12 10:29 | Silvia.Horvatova | Silvia Horvatova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | race, tax |  | Zuzana.Benedikova |  | 8 | 1600 | 996.75 | Default Location | Create
FHSTRWEPOWK-28 | SK - RWE Corporate Solutions 2026 - Alzbetka | 3 | 2026-05-12 11:22 | KollarcikovaA | Kollarcikova Alzbeta | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | 131899 |  | Zuzana.Benedikova |  | 3 | 1600 | 1386 | Default Location | Create
FHSTRWEPOWK-28 | SK - RWE Corporate Solutions 2026 - Alzbetka | 2 | 2026-05-12 12:34 | KollarcikovaA | Kollarcikova Alzbeta | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | Definition Standard Changes CO/PS, Follow Up: CITS Value-Stream-Orientation - Agile Structure, Chapter Controlling / interne Abstimmung |  | Zuzana.Benedikova |  | 2 | 1600 | 1386 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 1 | 2026-05-12 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP SF |  | Zuzana.Benedikova |  | 1 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 6.5 | 2026-05-12 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP AUTH HBA & IT Audit |  | Zuzana.Benedikova |  | 6.5 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 2.5 | 2026-05-12 15:16 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | GLOBAL SP6-ID 131824 FI-AA: New KeyFigure Group Z001 |  | Zuzana.Benedikova |  | 2.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 2.5 | 2026-05-12 15:18 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | Global SP6-ID 131985 FI-AA: Erweiterung RWE FIORI Asset Histo - Extention - PS-Fields |  | Zuzana.Benedikova |  | 2.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-23 | SK - RWE Corporate Solutions 2026 - Veronika M. | 2 | 2026-05-13 10:00 | Veronika.Mikulakova | Veronika Mikulakova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | 131018 - 2 hod |  | Zuzana.Benedikova |  | 2 | 1600 | 1489 | Default Location | Create
FHSTRWEPOWK-30 | SK - RWE Corporate Solutions 2026 - Silvia | 6.5 | 2026-05-13 10:29 | Silvia.Horvatova | Silvia Horvatova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | race, tax |  | Zuzana.Benedikova |  | 6.5 | 1600 | 996.75 | Default Location | Create
FHSTRWEPOWK-31 | SK - RWE Corporate Solutions 2026 - Kubo | 4 | 2026-05-13 10:32 | Jakub.Martinek | Jakub Martinek | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SM131032 |  | Zuzana.Benedikova |  | 4 | 1600 | 1542 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 1 | 2026-05-13 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP SF |  | Zuzana.Benedikova |  | 1 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 6.5 | 2026-05-13 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP AUTH HBA & IT Audit |  | Zuzana.Benedikova |  | 6.5 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 2.5 | 2026-05-13 15:14 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | GLOBAL SP6-ID 131824 FI-AA: New KeyFigure Group Z001 |  | Zuzana.Benedikova |  | 2.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1.5 | 2026-05-13 15:15 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | Global SP6-ID 131985 Extention; Asset-History-Sheet - Analyse / PS-Fields |  | Zuzana.Benedikova |  | 1.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1 | 2026-05-13 15:16 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | Lola - KT - Mentoring Effort Estimation for Off-Shore Team - White-List Changes |  | Zuzana.Benedikova |  | 1 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 0.75 | 2026-05-13 15:16 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO INC01493961 RP4_100 RE-FX/AA: Datum ÜWE auslösen (Liegenschaftsmanagement) - Fehler Mengenermittlung |  | Zuzana.Benedikova |  | 0.75 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1 | 2026-05-14 08:57 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | Global SP6-ID 131985 FI-AA: Erweiterung RWE FIORI Asset Histo - Extention |  | Zuzana.Benedikova |  | 1 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-29 | SK - RWE Corporate Solutions 2026 - Roman | 1 | 2026-05-14 09:19 | Roman.Kroupa | Roman Kroupa | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | IN PROGRESS | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SM131655 |  | Zuzana.Benedikova |  | 1 | 1600 | 1452.5 | Default Location | Create
FHSTRWEPOWK-30 | SK - RWE Corporate Solutions 2026 - Silvia | 2 | 2026-05-14 10:27 | Silvia.Horvatova | Silvia Horvatova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | tax |  | Zuzana.Benedikova |  | 2 | 1600 | 996.75 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 1 | 2026-05-14 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP SF |  | Zuzana.Benedikova |  | 1 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 6.5 | 2026-05-14 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP AUTH HBA & IT Audit |  | Zuzana.Benedikova |  | 6.5 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-27 | SK - RWE Corporate Solutions 2026 - Dasa | 4 | 2026-05-14 13:49 | Dasa.Krompaska | Dasa Krompaska | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | CITS AddServ RES- SM0000131876- 2 CITS/SAP Core Rx4 add.Serv.- Organisation- 2 |  | Zuzana.Benedikova |  | 4 | 1600 | 1329 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 3 | 2026-05-14 15:14 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | GLOBAL SP6-ID 131824 FI-AA: New KeyFigure Group Z001 |  | Zuzana.Benedikova |  | 3 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1.5 | 2026-05-15 08:55 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | Global SP6-ID 131985 FI-AA: Erweiterung RWE FIORI Asset Histo |  | Zuzana.Benedikova |  | 1.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1 | 2026-05-15 08:59 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO Rx4 - INC01480850 Dumps Analyse RS4_100, Doc |  | Zuzana.Benedikova |  | 1 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-30 | SK - RWE Corporate Solutions 2026 - Silvia | 4 | 2026-05-15 10:27 | Silvia.Horvatova | Silvia Horvatova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | tax, race |  | Zuzana.Benedikova |  | 4 | 1600 | 996.75 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 1 | 2026-05-15 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP SF |  | Zuzana.Benedikova |  | 1 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 6.5 | 2026-05-15 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP AUTH HBA & IT Audit |  | Zuzana.Benedikova |  | 6.5 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 3 | 2026-05-18 08:54 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | Global SP6-ID 131985 FI-AA: Erweiterung RWE FIORI Asset Histo |  | Zuzana.Benedikova |  | 3 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 2 | 2026-05-18 08:58 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO Rx4 - INC01480850 - Dumps Analyse RS4_100 |  | Zuzana.Benedikova |  | 2 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 1 | 2026-05-18 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP SF |  | Zuzana.Benedikova |  | 1 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 6.5 | 2026-05-18 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP AUTH HBA |  | Zuzana.Benedikova |  | 6.5 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-22 | SK - RWE Corporate Solutions 2026 - Lien | 1 | 2026-05-18 16:08 | lien.nguyenthi | Thi Lien Nguyen | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | INC01494810/131890, RP4_100 New RID-933390 to/RWE4/OM_CUST_I |  | Zuzana.Benedikova |  | 1 | 1600 | 1560 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 1 | 2026-05-19 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP SF |  | Zuzana.Benedikova |  | 1 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-33 | SK - RWE Corporate Solutions 2026 - Vierka | 6.5 | 2026-05-19 12:47 | Viera.Mrazova | Viera Mrazova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | SAP AUTH HBA |  | Zuzana.Benedikova |  | 6.5 | 1600 | 954 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 0.75 | 2026-05-19 15:27 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | KTLO - INC01500131 RP4_100 RE-FX: Fehler bei Transaktion /RWE4/REFXAA_KAUFPR – Anteiliger Kaufpreis Anlage |  | Zuzana.Benedikova |  | 0.75 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-24 | SK - RWE Corporate Solutions 2026 - Gabika | 1.5 | 2026-05-19 15:28 | Gabriela.Princova | Gabriela Princova | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | Global SP6-ID 131985 Extention; Asset-History-Sheet - Analyse / PS-Fields |  | Zuzana.Benedikova |  | 1.5 | 1600 | 0 | Default Location | Create
FHSTRWEPOWK-22 | SK - RWE Corporate Solutions 2026 - Lien | 1 | 2026-05-19 16:12 | lien.nguyenthi | Thi Lien Nguyen | 0526 | [5 empty] | RWE Corporate Solutions 2025 FSK ERP FHS |  |  |  | Task | TO DO | FHSTRWEPOWK | RWE Corporate Solutions 2025 FSK ERP FHS |  |  | INC01466432/CR 131147: field Tax Currency Translation needs to be changed from 1 to 5 for PL company codes. |  | Zuzana.Benedikova |  | 1 | 1600 | 1560 | Default Location | Create

## Users
Full name | Username | Worked | Billable | Planned | Required | Progress | Period (2026-04-06 - 2026-05-05) | Period (2026-05-06 - 2026-06-05) | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31
Jakub Martinek | Jakub.Martinek | 6 | 6 | 0 | 152 | 4 | Open | Open | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kollarcikova Alzbeta | KollarcikovaA | 10.5 | 10.5 | 0 | 152 | 7 | Open | Open | 0 | 0 | 0 | 0.5 | 1.5 | 0 | 0 | 3 | 0 | 0 | 0.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Silvia Horvatova | Silvia.Horvatova | 61 | 61 | 0 | 152 | 40 | Open | Open | 0 | 0 | 0 | 6.5 | 8 | 7 | 3 | 8 | 0 | 0 | 8 | 8 | 6.5 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Veronika Mikulakova | Veronika.Mikulakova | 4 | 4 | 0 | 152 | 3 | Open | Open | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Thi Lien Nguyen | lien.nguyenthi | 6 | 6 | 0 | 152 | 4 | Open | Open | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Viera Mrazova | Viera.Mrazova | 82.5 | 82.5 | 0 | 152 | 54 | Open | Open | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gabriela Princova | Gabriela.Princova | 39.75 | 39.75 | 0 | 152 | 26 | Open | Open | 0 | 0 | 0 | 2.25 | 2.5 | 2.5 | 2 | 2.5 | 0 | 0 | 3.5 | 5 | 5.75 | 4 | 2.5 | 0 | 0 | 5 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Roman Kroupa | Roman.Kroupa | 5 | 5 | 0 | 152 | 3 | Open | Open | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dasa Krompaska | Dasa.Krompaska | 20 | 20 | 0 | 152 | 13 | Open | Open | 0 | 0 | 0 | 2 | 2 | 2 | 4 | 4 | 0 | 0 | 2 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0